## 7300-010
Software Release Procedure
7300-010 | This document is the work instruction for releasing software to production. It is assumed that all necessary engineering, manufacturing and customer verification/validation has been completed.
| 1 | AFFECTED AREAS
This procedure applies to personnel within the Watlow Winona organization who are involved in aspects of releasing software for production, based on product and customer requirements.
3 Pages
| 2 | DEFINITIONS
Revision Level: E
0500 - A part number specifying a software item 0500-<family>-<version>
Document Control - A document control function that is centralized.
ECO - Engineering Change Order.
Existing Product - Product that is currently in the Watlow Winona product offering.
Item Master (IM) - Form used for creating a new Watlow part number.
Master Part - A programmed chip that acts as the reference for all programmed parts.
Output Items - The final results of the software process such as binary, hex, s19, or flash files.
Product Manager - Marketing person responsible for a product or product line.
Part Master - A method to entering a specific version part number in the document system
Part Qual - A method of entering a software part family into the document system.
Release Record - The checklist that captures all the artifacts generated as proof of release duties.
SML - Software Maintenance Log, the offical print for a 0500 software item.
Verification Release Memo - A document from the test group indicating the released software meets the documented expectations.
Version Control System - System used to maintain and label software projects and history.
| 3 | ASSOCIATED DOCUMENTS
| 7300-023 | Glossary of Product Development Terms
| 7310-001 | P Number Form
| 7320-001 | Item Master Request
| 7330-003 | Software Maintenance Log Form
On-line ECO Process
| 4 | PROCEDURE
Note 1: The current location for flash images is O:\Flash

## Release Record
Software Release Record
|  | Template Revision | Description | Date
|  | F | From Word format | 2008-02-01
|  | G | Rolled into Excel | 2008-02-15
Complete this form for each release following 7300-010
| Software Version |  | 19.00.102
| Product Name: |  | Percival Gen II Intellus
| ECO or Item Master: |  | ECO 16005
| Account/Product Manager: |  | Steve Burt
| Project Team Members: |  | Cathy Wade
| Date: |  | 12/08/16
Summary of Changes
Description of Changes
| 1 | Added XML tags for the Digital Input Door Duration and Bluetooth Enable.
| 2 | Added defrost indication on first display loop in place of the time.
| 3 | Fixed time display for DLI or Diurnal in Elapsed mode on the Monitor web page.
| 4 | Fixed light entry focus to stay on a box if an incorrect value is entered on the Program Edit web page.
| 5 | Fixed light output numbering in the status section of e-mails.
| 6 | Fixed issue with copying a program and then editing it, the edit would look like the new program but would actually change the original.
| 7 | Added the RM slot types to the head of the configuration file to prevent the case where a logic source could have been configured to an RM source before the slot types were set. This allows the display list to be adjusted based on the slot type.
| 8 | Fixed the configuration file functions to use the XML parameters in three ways, Ignore, Save Only, Save/Restore. Updated the spec embedded file “Complete XML Tag List.xlsx” with an additional column which defines the configuration file action for each parameter.
| 9 | Added Active_Gateway and Active_Subnet to the XML tags to show the active values. The Default_Gateway and Subnet_Mask are used to write the fixed values.
| 10 | Added RMC closed loop lighting choices for AIN_LIGHT and SP_LIGHT for the RM control loops 4-7.
| 11 | Added RMC CHA_POWER DALI power sources for the RM control loops 4-7.
| 12 | Changed e-mail light status title.
| 13 | Fixed logic source visibility for the RM loops.
| 14 | Required that DALI sources for CHA have a corresponding logic source.
| 15 | Fixed incrementing programmed lights and lights on for closed loop light sources.
| 16 | Changed one XML tag to SaveOnly.
| 17 | Fixed issue with alarm disable not taking effect without a power cycle.
| 18 | Change setup exit keys to Up/Down, incorrectly was Enter/Up.
| 19 | Changed defaults for RH channel output overrides.
| 20 | Changed default names for the RM inputs.
| 21 | Increased the maximum propband to 9999.
| 22 | Fixed issue with the timing of the SD card vendor ID for functional test.
| 23 | Fixed issue with display of Light On Time for logic outputs tied to lights.
| 24 | DLI on other inputs seems to be working.
| 25 | Added selectable DLI source in code and web pages.
| 26 | Fixed issue with displaying alarm setpoints for High or Low sides only.
| 27 | Reverted lib_mem.c and fs_buf.c to Micrium's version to fix file corruption issue.
| 28 | Fixed the Bluetooth enable to be based on the parameter shown in the user global menu. Both the Bluetooth.xml and the Bluetooth_Enable= Yes commands have the same functionality, but the Bluetooth.xml command will respond with more detailed error checking if the enable didn’t seem to work correctly.
| 29 | Fixed issues with the end setpoint calculations in both 24 hour and elapsed ramping.
| 30 | Fixed cloud header to correctly use the display units when any sensor input is set to RTD.
| 31 | Fixed incorrect alarm displays on web page.
| 32 | Also fixed display loop which showed both E20 and High Limit 2 displays for a Limit 2 sensor error.
| 33 | Fixed incorrect display of DLI night setpoint for the CLP selected for the DLI input.
| 34 | Added override of 0.0 for the night setpoint for the CLP selected for the DLI input.
| 35 | Added test to WatbusLink to reset the state machine if no receives are detected within 1 second. This fixes an issue seen with the debugger and may also fix any Watbus lock ups that happen in real time. The file corruption bug was caused by a change to the file system drivers and was stated to prevent lengthy interrupt disables that supposedly locked up Watbus. Hopefully this will handle that problem if it ever occurs in the field. The data stale that would come up if Watbus was stopped temporarily occurs after 3 seconds, so the user shouldn't see any changes if this occurs with the reset after 1 second of no comms.
| 36 | Updated DALI equation per customer request.
| 37 | Fixed issues with characters in the XML parser, on the web pages and in the program names.
| 38 | Fixed issue in XML datalog transfer related to leap year.
Software Modules Affected
Many including some of the web page files which will be released to 2.00
Compatibity and impact of the new software
When the user updates the software full defaults may occur.
Output Items
| Type | Filename | Description | Watlow Part Number
| s19 | app.s19 | Application binary image | NA
| bin | PercivalAppArm.bin | USB flashloader image | NA
| s19 | PercivalAppArm.s19 | Serial flashloader image | NA
| hex | 0500-3205-1900_102.hex | Full combined binary image | 0500-3205-1900
Tools Used
| IDE | (Compiler, Libraries, Linker, Debugger) | IAR 6.50.6
| RTOS |  | Micrium
| Make Utility |  | NA
| Special Utilities |  | NA
| Post Processors |  | PostProcess.bat
| Flash File Builder |  | PostProcess.bat
| Build Instruction File |  | NA
Version Identification
| Source Code Label |  | Released Revision 19.00.102
| SRS Baseline |  | Revision C
Release Activities
| 1 | V&V release memo obtained
| 2 | Source Files are checked into Version Control
| 3 | SML Updated and in Version Control
| 4 | Output Items are archived
| 5 | Source Files are labelled in Version Control
| 6f | For FLASH parts, Output Items are distributed
| 6p | For programmed parts verify master
| 7 | SRS updated
| 8 | Customer / Product Management notified
| 9 | This document in version control
Artifacts
1. Release Memo
Insert V&V memo as embedded file
Customer signed off after evaluation
2. Source Files in Version Control
Insert screen capture of source files in version control
3. SML Update and in Version Control
NA
4. Outputs Items archived
Insert a screen capture of the output items in version control
5. Source Files Labelled
Insert copy of SRS status
6f. Output Items distributed to FLASH location
NA
6p. Checksum comparison record (programmed parts)
NA
7. Specification Updated/Released
NA
8. Customer or Product Manager Notified
NA
9. This document in version control

## Document Descriptions
Documents Defintions
Software Part Number |  | 0500-PPPP-VVVV
Software is described in the business and document control systems as 0500-PPPP-VVVV where PPPP is the unique software identifier and VVVV is the version. The 0500 number is pulled from the file room. It is unique for a product or version of the product. Each different compilation requires a new 0500 number. For instance 2 versions of a product have the same project file but different compilation switches to handle different feature sets or hardware options. This requires different 0500 numbers. Custom versions of a product require different 0500 numbers. The key driver is manufacturing. They need a uniquely identifiable software component to put into the product for any configuration of a product.
SML |  | 7330-003
The SML (Software Maintenance Log) is the revision print for the software. By its nature software does not have any visible means for identification. The SML identifies the current software revision of a 0500 number. The revision of the SML itself is an alpha revision. The SML has a document print revision level A,B,C; the 0500 has a product software version revision. The 0500 revision follows the Watlow Software Version Number for standard and custom products. The last 4 digits are MMmm major (m) and minor (m) revision. Therefore version 3.00 is 0500-xxxx-0300. ThermoKing uses the TK revision standard 0500-xxxx-6502 or 0500-xxxx-B002.
Software Release Document |  | 7300-045
The Software Release Document is a record of the release.
It also contains the artifacts of the release:
Summary of the change
Impact and compatibility of the change
Build process
Tools used
Participants
ECO linkage
Embedded V&V release memo
Screen capture of Source Control duties - Check-in, labeling, outputs archived etc
Screen capture of distribution of outputs to correct locations
Part Qualification |  | 0500-PPPP-xxxx
Create a part qualification after pulling a new 0500 number from document control. The part qualification defines the base 0500-PPPP-xxxx number family. The revision field is xxxx to be filled by future part masters.
Part Master |  | 0500-PPPP-MM00
For each revision of software (i.e. SML change) create a part master for the new MM00. For version 4 of a product create a part master for 0500-PPPP-0400. Because the SML is an official print, a Part Master is all that is needed for the new 0500 revision number. This is very easy and streamlined.
BOM |  | XXXX-XXXX-XXXX
The BOM needs to call out the 0500 number to define which software gets installed in which manufactured assembly. Given different assembly or top level numbers it is possible to be selling 2 different versions of a product with different revs of the same 0500. Example: Z100-OLD1-0000 contains 0500-1111-0100 and Z100-NEW1-0000 contains 0500-1111-0200. This would allow manufacturing of service parts at past stages of the product’s life cycle.
Products that use programmed physical parts should have a sub assembly that combines the 0500 with the blank part. A 0805-1234-0001 BOM will combine a blank 0805-1234-0000 part plus a 0030-xxxx-0200 printed label and a 0500-9999-0200 software revision. Flash loaded assemblies will combine a populated board with a 0500 at the assembly BOM or configurator level.
Procedure List
| 0500 Part Qual |  | Instructions
| 0500 Part Master |  | Instructions
| Software Release Procedure 7300-010 |  | Procedure
| Software Release Record with artifacts. |  | Record
| ECO IM Duties |  | Instructions
| Document and SRS archival |  | Instructions
| Example of a completed release record |  | Example

## Part Qual Details
Part Qual Process for Software
“Fill Out This Form”
General Sheet
Part Qual Page
Approvals
None needed, the SML will get approved.
Click "Submit"

## Part Master Details
Part Master Process for Software
“Fill Out This Form”
General Screen
Part Master Page
The Product Class, Sub Class, Rev Level, Accounting code are product specific.
Approvals
None needed, the SML will get approved.
Submit

## Software Archive Procedure
Software Release Archiving Instructions
The software source code is in Visual Source Safe. That is the source. A zipped snap shot is useful for base lining in document control.
For the archiving duties, include this group of documents. Approvals are Design Engineering (required), Project Management (optional), and Product Management (optional)
SRS archive
Export the SRS from DOORS.
Attach the SRS coversheet. 7300-075.doc

## Example Record
EXAMPLE: Software Release Record
|  | Template Revision | Description | Date
|  | F | From Word format | 2008-02-01
|  | G | Rolled into Excel | 2008-02-15
Complete this form for each release following 7300-010
| Software Version |  | 3.00.23
| Product Name: |  | EZ-Zone FU
| ECO or Item Master: |  | ECO 12345
| Account/Product Manager: |  | John Griggs
| Project Team Members: |  | Bob Moran, Bob Greener
| Date: |  | 1/1/2001
Summary of Changes
Description of Changes
| 1 | Added a fudge factor | Issue 123
| 2 | Added the DUH prompt | New Feature
Software Modules Affected
Everything.c
MaxedOut.h
Compatibity and impact of the new software
If the user updates from 1.00 all the full defuaults will occur.
If the user updates from 2.00 the buad rate will be reset, all else is OK.
Compatible with TroubleMaker.exe
Output Items
| Type | Filename | Description | Watlow Part Number
| s19 | FlameGrill.s19 | Final Image | 0500-6000-0300
| flh | FlashFlash | Field FLASH file | na
Tools Used
| Compiler(s) |  | IAR
| Compiler Version |  | 1.1
| Linker and Locator |  | 1.1g
asdasdsadasasd
| Libraries |  | Micrium Modbus
| RTOS |  | RTXC 1.2
| Make Utility |  | FlameBuilder.exe
| Special Utilities |  | Douse.exe
| Post Processors |  | Ashes.exe
| Flash File Builder |  | TrenchCoat.exe
| Build Instruction File |  | HowIDidIt.doc
Version Identification
| Source Code Label |  | Version 3.00.23
| SRS Baseline |  | Baseline 4
Release Activities
| 1 | V&V release memo obtained
| 2 | Source Files are checked into Version Control
| 3 | SML Updated and in Version Control
| 4 | Output Items are archived
| 5 | Source Files are labelled in Version Control
| 6f | For FLASH parts, Output Items are distributed
| 6p | For programmed parts verify master
| 7 | SRS updated
| 8 | Customer / Product Management notified
| 9 | This document in version control
Artifacts
1. Release Memo
Insert V&V memo as embedded file
2. Source Files in Version Control
Insert screen capture of source files in version control
Application
Booloader
3. SML Update and in Version Control
Insert SML as embedded file
4. Outputs Items archived
Insert a screen capture of the output items in version control
5. Source Files Labelled
Insert screen capture of version label from version control
6f. Output Items distributed to FLASH location
Insert a screen capture of the output items in the distribution location
6p. Checksum comparison record (programmed parts)
Insert screen capture of the checksum screen or checksum value
NA
7. Specification Updated/Released
Insert copy of SRS status
8. Customer or Product Manager Notified
Insert copy of notification communication (email etc)
9. This document in version control

## ECO IM Duties
ECO / Item Master Duties
| Execute procedure 7300-010 | Procedure
| Archive Electronic Files | Instructions
If specs changes, archive SRS too
| Master Documents Signed | Approve Archival