## 7300-010
Software Release Procedure
7300-010 | This document is the work instruction for releasing software to production. It is assumed that all necessary engineering, manufacturing and customer verification/validation has been completed.
| 1 | AFFECTED AREAS
This procedure applies to personnel within the Watlow Winona organization who are involved in aspects of releasing software for production, based on product and customer requirements.
3 Pages
| 2 | DEFINITIONS
Revision Level: E
0500 - A part number specifying a software item 0500-<family>-<version>
Document Control - A document control function that is centralized.
ECO - Engineering Change Order.
Existing Product - Product that is currently in the Watlow Winona product offering.
Item Master (IM) - Form used for creating a new Watlow part number.
Master Part - A programmed chip that acts as the reference for all programmed parts.
Output Items - The final results of the software process such as binary, hex, s19, or flash files.
Product Manager - Marketing person responsible for a product or product line.
Part Master - A method to entering a specific version part number in the document system
Part Qual - A method of entering a software part family into the document system.
Release Record - The checklist that captures all the artifacts generated as proof of release duties.
SML - Software Maintenance Log, the offical print for a 0500 software item.
Verification Release Memo - A document from the test group indicating the released software meets the documented expectations.
Version Control System - System used to maintain and label software projects and history.
| 3 | ASSOCIATED DOCUMENTS
| 7300-023 | Glossary of Product Development Terms
| 7310-001 | P Number Form
| 7320-001 | Item Master Request
| 7330-003 | Software Maintenance Log Form
On-line ECO Process
| 4 | PROCEDURE
Note 1: The current location for flash images is O:\Flash

## Release Record
Software Release Record
|  | Template Revision | Description | Date
|  | F | From Word format | 2008-02-01
|  | G | Rolled into Excel | 2008-02-15
Complete this form for each release following 7300-010
| Software Version |  | 21.00.111
| Product Name: |  | Percival Gen II Intellus
| ECO or Item Master: |  | ECO 16117
| Account/Product Manager: |  | Steve Burt
| Project Team Members: |  | Cathy Wade
| Date: |  | 6/27/17
Summary of Changes
Description of Changes
| 1 | NOTE: Change to Micrium driver file!!!!
| 2 | This change was required because some SD cards did not report size information as expected.
Software Modules Affected
fs_partition.c
Compatibity and impact of the new software
When the user updates the software full defaults may occur.
Output Items
| Type | Filename | Description | Watlow Part Number
| s19 | app.s19 | Application binary image | NA
| bin | PercivalAppArm.bin | USB flashloader image | NA
| s19 | PercivalAppArm.s19 | Serial flashloader image | NA
| hex | 0500-3205-2100_111.hex | Full combined binary image | 0500-3205-2100
Tools Used
| IDE | (Compiler, Libraries, Linker, Debugger) | IAR 6.50.6
| RTOS |  | Micrium
| Make Utility |  | NA
| Special Utilities |  | NA
| Post Processors |  | PostProcess.bat
| Flash File Builder |  | PostProcess.bat
| Build Instruction File |  | NA
Version Identification
| Source Code Label |  | Released Revision 21.00.111
| SRS Baseline |  | Revision C
Release Activities
| 1 | V&V release memo obtained
| 2 | Source Files are checked into Version Control
| 3 | SML Updated and in Version Control
| 4 | Output Items are archived
| 5 | Source Files are labelled in Version Control
| 6f | For FLASH parts, Output Items are distributed
| 6p | For programmed parts verify master
| 7 | SRS updated
| 8 | Customer / Product Management notified
| 9 | This document in version control
Artifacts
1. Release Memo
Insert V&V memo as embedded file
Customer signed off after evaluation
2. Source Files in Version Control
Insert screen capture of source files in version control
3. SML Update and in Version Control
NA
4. Outputs Items archived
Insert a screen capture of the output items in version control
5. Source Files Labelled
Insert copy of SRS status
6f. Output Items distributed to FLASH location
NA
6p. Checksum comparison record (programmed parts)
NA
7. Specification Updated/Released
NA
8. Customer or Product Manager Notified
NA
9. This document in version control

## Document Descriptions
Documents Defintions
Software Part Number |  | 0500-PPPP-VVVV
Software is described in the business and document control systems as 0500-PPPP-VVVV where PPPP is the unique software identifier and VVVV is the version. The 0500 number is pulled from the file room. It is unique for a product or version of the product. Each different compilation requires a new 0500 number. For instance 2 versions of a product have the same project file but different compilation switches to handle different feature sets or hardware options. This requires different 0500 numbers. Custom versions of a product require different 0500 numbers. The key driver is manufacturing. They need a uniquely identifiable software component to put into the product for any configuration of a product.
SML |  | 7330-003
The SML (Software Maintenance Log) is the revision print for the software. By its nature software does not have any visible means for identification. The SML identifies the current software revision of a 0500 number. The revision of the SML itself is an alpha revision. The SML has a document print revision level A,B,C; the 0500 has a product software version revision. The 0500 revision follows the Watlow Software Version Number for standard and custom products. The last 4 digits are MMmm major (m) and minor (m) revision. Therefore version 3.00 is 0500-xxxx-0300. ThermoKing uses the TK revision standard 0500-xxxx-6502 or 0500-xxxx-B002.
Software Release Document |  | 7300-045
The Software Release Document is a record of the release.
It also contains the artifacts of the release:
Summary of the change
Impact and compatibility of the change
Build process
Tools used
Participants
ECO linkage
Embedded V&V release memo
Screen capture of Source Control duties - Check-in, labeling, outputs archived etc
Screen capture of distribution of outputs to correct locations
Part Qualification |  | 0500-PPPP-xxxx
Create a part qualification after pulling a new 0500 number from document control. The part qualification defines the base 0500-PPPP-xxxx number family. The revision field is xxxx to be filled by future part masters.
Part Master |  | 0500-PPPP-MM00
For each revision of software (i.e. SML change) create a part master for the new MM00. For version 4 of a product create a part master for 0500-PPPP-0400. Because the SML is an official print, a Part Master is all that is needed for the new 0500 revision number. This is very easy and streamlined.
BOM |  | XXXX-XXXX-XXXX
The BOM needs to call out the 0500 number to define which software gets installed in which manufactured assembly. Given different assembly or top level numbers it is possible to be selling 2 different versions of a product with different revs of the same 0500. Example: Z100-OLD1-0000 contains 0500-1111-0100 and Z100-NEW1-0000 contains 0500-1111-0200. This would allow manufacturing of service parts at past stages of the product’s life cycle.
Products that use programmed physical parts should have a sub assembly that combines the 0500 with the blank part. A 0805-1234-0001 BOM will combine a blank 0805-1234-0000 part plus a 0030-xxxx-0200 printed label and a 0500-9999-0200 software revision. Flash loaded assemblies will combine a populated board with a 0500 at the assembly BOM or configurator level.
Procedure List
| 0500 Part Qual |  | Instructions
| 0500 Part Master |  | Instructions
| Software Release Procedure 7300-010 |  | Procedure
| Software Release Record with artifacts. |  | Record
| ECO IM Duties |  | Instructions
| Document and SRS archival |  | Instructions
| Example of a completed release record |  | Example

## Part Qual Details
Part Qual Process for Software
“Fill Out This Form”
General Sheet
Part Qual Page
Approvals
None needed, the SML will get approved.
Click "Submit"

## Part Master Details
Part Master Process for Software
“Fill Out This Form”
General Screen
Part Master Page
The Product Class, Sub Class, Rev Level, Accounting code are product specific.
Approvals
None needed, the SML will get approved.
Submit

## Software Archive Procedure
Software Release Archiving Instructions
The software source code is in Visual Source Safe. That is the source. A zipped snap shot is useful for base lining in document control.
For the archiving duties, include this group of documents. Approvals are Design Engineering (required), Project Management (optional), and Product Management (optional)
SRS archive
Export the SRS from DOORS.
Attach the SRS coversheet. 7300-075.doc

## Example Record
EXAMPLE: Software Release Record
|  | Template Revision | Description | Date
|  | F | From Word format | 2008-02-01
|  | G | Rolled into Excel | 2008-02-15
Complete this form for each release following 7300-010
| Software Version |  | 3.00.23
| Product Name: |  | EZ-Zone FU
| ECO or Item Master: |  | ECO 12345
| Account/Product Manager: |  | John Griggs
| Project Team Members: |  | Bob Moran, Bob Greener
| Date: |  | 1/1/2001
Summary of Changes
Description of Changes
| 1 | Added a fudge factor | Issue 123
| 2 | Added the DUH prompt | New Feature
Software Modules Affected
Everything.c
MaxedOut.h
Compatibity and impact of the new software
If the user updates from 1.00 all the full defuaults will occur.
If the user updates from 2.00 the buad rate will be reset, all else is OK.
Compatible with TroubleMaker.exe
Output Items
| Type | Filename | Description | Watlow Part Number
| s19 | FlameGrill.s19 | Final Image | 0500-6000-0300
| flh | FlashFlash | Field FLASH file | na
Tools Used
| Compiler(s) |  | IAR
| Compiler Version |  | 1.1
| Linker and Locator |  | 1.1g
asdasdsadasasd
| Libraries |  | Micrium Modbus
| RTOS |  | RTXC 1.2
| Make Utility |  | FlameBuilder.exe
| Special Utilities |  | Douse.exe
| Post Processors |  | Ashes.exe
| Flash File Builder |  | TrenchCoat.exe
| Build Instruction File |  | HowIDidIt.doc
Version Identification
| Source Code Label |  | Version 3.00.23
| SRS Baseline |  | Baseline 4
Release Activities
| 1 | V&V release memo obtained
| 2 | Source Files are checked into Version Control
| 3 | SML Updated and in Version Control
| 4 | Output Items are archived
| 5 | Source Files are labelled in Version Control
| 6f | For FLASH parts, Output Items are distributed
| 6p | For programmed parts verify master
| 7 | SRS updated
| 8 | Customer / Product Management notified
| 9 | This document in version control
Artifacts
1. Release Memo
Insert V&V memo as embedded file
2. Source Files in Version Control
Insert screen capture of source files in version control
Application
Booloader
3. SML Update and in Version Control
Insert SML as embedded file
4. Outputs Items archived
Insert a screen capture of the output items in version control
5. Source Files Labelled
Insert screen capture of version label from version control
6f. Output Items distributed to FLASH location
Insert a screen capture of the output items in the distribution location
6p. Checksum comparison record (programmed parts)
Insert screen capture of the checksum screen or checksum value
NA
7. Specification Updated/Released
Insert copy of SRS status
8. Customer or Product Manager Notified
Insert copy of notification communication (email etc)
9. This document in version control

## ECO IM Duties
ECO / Item Master Duties
| Execute procedure 7300-010 | Procedure
| Archive Electronic Files | Instructions
If specs changes, archive SRS too
| Master Documents Signed | Approve Archival